Parish Council Meeting 8th January 2024 Item 191. Clavering PC Writing a Neighbourhood Plan

Appendix 3

Fact Finding Information via RCCE

- There is a requirement for a Planning Consultant to be on board.

- The PC would obviously need to approach 3 for quotes for the work required.

How to start..

I was given to understand that the resources here are available at no further cost to CPC as members of RCCE

https://www.essexrcc.org.uk/clp-network-resources

Grant Available:

https://neighbourhoodplanning.org/about/grant-funding/

There is a £10k Basic Grant, plus £8k Additional Grant (which we will qualify to receive if we include Design Codes in your NP – which we will do), plus Technical Support Packages.

It’s a 2 stage process: submit an Expression of interest and then receive a link to the full online application.

As mentioned, the grant is for the year 2023/24

Per the website:

Applications for grant and technical support for the 2023/2024 financial year can be submitted until 5pm on 26th January 2024. Any applications received after this time will not be considered. We will also not be able to consider incomplete applications, so please read our guidance notes carefully.

If there is a high volume of applications for grant and technical support, it may be necessary to prioritise applications.

For grant this means considering applications on a first come first served basis. If your grant application is incomplete, or does not meet the eligibility requirements, it will not be considered. Please note, expenditure met through a grant must be completed on or before 31st March 2024.

It appears that to apply for this grant means that CPC must set up a Committee to form the Steering Group and have all completed and invoiced by 31st March 2024.

Opinion of CPC Chairman is that this is not possible as we have not even started a formal consultation.

It should be there has been no confirmation from the Government that grant funding will made available for 2024-2025

Scope of work

Suggested Scope of Work for Consultant

Stage 1. Plan Preparation.

1. Review vision and objectives as they emerge from the ongoing Community Consultation and ensure they meet the criteria of being clear and concise.

2. Prepare a framework for the Neighbourhood Plan to include information about the village today and a summary of evidence that already exists that can be used to inform policy. Eg Shalford PC intended to commission a Landscape Character Assessment and to obtain the free technical support packages for Housing Needs Assessment and Design Codes.

3. Advise on areas where further evidence is needed and where additional studies should be undertaken. Support the NP steering group to undertake or commission such studies.

NOTE: RCCE can support the NP steering group with engaging the community, but advice may be welcome on the wording of specific questions in surveys.

4. Draft the plan policies, clearly supported by, and related to, sufficient evidence. Confirm that policies and community actions / aspirations are clearly delineated.

5 Confirm whether there is a requirement for a Strategic Environmental Assessment or Habitats Regulations Appraisal for our plan.

6 Confirm that the plan in your opinion will meet the requirements of the Basic Conditions

Stage 2. Pre-Submission Consultation (Regulation 14)

None

Stage 3. Post consultation and Submission to Local Authority

1. Review and advise on changes resulting from Pre- Submission consultation responses and support preparation of the Submission Draft Plan

2. (a) Prepare the Consultation Statement; or

(b) Review and advise on the Consultation Statement prepared by the Steering Group

3. Prepare the Basic Conditions Statement

Stage 4. Publicity (Regulation 16)

None

Stage 5. Independent Examination

1. Ad Hoc Support to assist in answering clarification requests from Examiner if required.

Stage 6. Referendum

None

Stage 7. Implementation

Note. This stage will be supplementary to the contract and the reimbursable rates should be identified as a separate cost to cover this service on request.

Recommendation.

Invitation issued to those wishing to be part of a Clavering Neighbourhood Plan Steering Group (NPSG). Meetings hosted and members of other NPSG invited to give a short presentation & advice.

Resources at RCCE utilised throughout.

Cllr Stephanie M Gill 30th December 2023